## Sheet1
Ice Berg Chart
CS 2450
F. Colton Parry
Karl Schuelke
Michael Kennard
Scott Weber
Task No | Task Name | Priority | Duration | Elapsed Time
1 | ( C ) Book | H | 5 days
2 | ( D ) Data Members |  | 5 days
3 | ( C ) Patron | H | 5 days
4 | ( D ) Data Members |  | 5 days
5 | ( C ) Date | H | 5 days
6 | ( D ) Data Members |  | 5 days
7 | ( C ) File I / O | H | 5 days
8 | (F) Open Library File |  | 5 days
9 | (F) Save Library File |  | 5 days
10 | ( C ) Library | H | 7 days
11 | ( D ) Data Members |  | 7 days
12 | (F) Input Book |  | 7 days
13 | (F) New Patron |  | 7 days
14 | (F) ouputBookFile |  | 7 days
15 | (F) outputPatronFile |  | 7 days
16 | (F) checkoutBook |  | 7 days
17 | (F) checkinBook |  | 7 days
18 | (F) displayBooks |  | 7 days
19 | (F) displayPatrons |  | 7 days
20 | (F) addBook |  | 7 days
21 | (F) removeBook |  | 7 days
22 | (F) addPatron |  | 7 days
23 | (F) removePatron |  | 7 days
24 | ( C ) File I / O | M | 7 days
25 | (F) Open Library File |  | 7 days
26 | (F) Save Library File |  | 7 days
27 | Testing | M | 13 days
28 | Use Cases |  | 13 days
29 | Tests |  | 13 days
30 | GUI | L | 17 days
31 | Command Line Interface |  | 1 day?
32 | Graphical Interface |  | 7 days